## Sheet1
Time | Duration | Tasks | Notes | Remarks
Baishak 29 – Jestha 1 | 4 | Collect test samples for Words: Batti, Pankha, Samaya, Mausam, Sangeet Sentences: Batti ko awastha badala, Pankha ko sthiti badala, Aba ko samaya sunau, Aaja ko Mausam batau, Euta Sangeet bajau | Mentally, Mouthed and Audible mode
Jestha 2 – Jesth 6 | 4 | Analyse the collected samples. Decide which muscles to select. Decide the requirements like choosing the length of recordings, no. of recordings, modes, words or sentences | Jestha 6 for evaluating or summing up the whole finding. This time task can be extended up to 7 or 8
Jestha 7 – Jesth 8 | 2 | Generate summary of finding and plan for the clean recording of data
Jestha 9 – Jesth 12 | 4 | Start collecting the final data for training and testing. No. of users: 2 (for now) No. of samples per word/sentence: 200 (total sessions) No. of sessions: 4 (at least)
Jestha 13 – Jestha 15 | 3 | check the quality of collected data, recollect if necessary File type: json, pickle (any one) Format: Dictionary | If possible start preprocessing of data and store it
Jestha 16 – Jestha 19 | 4 | Start preprocessing, training and testing models. Preprocessing: Filter order and BW, Pipeline, Spectral Features: Spectrogram, MFCC Model: CNN
Jestha 21 – Jestha 22 | 2 | Generate finding if possible otherwise train and test | Jestha 20 is for evaluation
Jestha 23 – Jestha 26 | 4 | Evaluate the whole work, and will make plans based on results | Lets proceed based on the result achieved till this time